## HBL Strategy (hidden)
Harmonisation Baseline - Strategy for Update and Maintenance
Overall Strategy
1 | Refresh existing Baseline on which to lay down accumulated and emerging changes
Reconcile published and later versions of individual baseline elements and merge VLC & Data Codes
(See Strategy and approach below for each of the current baseline elements to address above issue)
Incorporate any omissions/errors in existing materials as they arise
Agree new baseline with all internals
2 | Apply accumulated changes since original baseline
See list from TO'N overleaf - appear to be mostly additions of codes and the like
Need quick survey to ensure comprehensiveness of this list
Agree new baseline with all internals
3 | Apply emerging Market Change related changes, both NI and ROI
See list overleaf - magnitude of changes varies; majority of NI-sourced changes may not be big hit on ROI elements
ROI-originated changes will be limited between now and golive
No. | Baseline Component | MCR1002 (ROI) - published 28 Jun 2010 | NI Email - 28 Jan 2010 | Other Sources (various dates) | Strategy | Actions Needed
1 | Market Messages (15 docs) | V3 Dates differ but are mostly 14 Dec 2009 (14 files). Files were delivered from NI team on 21 Jan | V5 Larger file sizes than V3 Differences appear to be mostly spelling corrections (14 files) | Technical V5 - 9 Mar 2010 (1 file) Note: No sign of any V4 files with CG or in RMDS inbox | Adopt V5 as master (incl. Technical) | Reconcile V3->V5 Determine correct version of 4 suspects (De-reg, FW Responses, Obj and Can, SONI) DONE - will take 28th Jan dated files in all cases
2 | Data Definitions | V1 (102 KB) Approx. 200 ROI defs and 20 NI defs. | V5 (217 KB) Differences are extra rows and columns | N/A | Adopt V5 as master | Confirm new strategy OK with NI. AGREED
3 | Data Codes | V1 (172 KB) Includes ALL coded fields, with special ref to ROI changes (5 cases) and new NI-derived codes (28 cases) | N/A (but see VLC below) | V1 (but at 178 KB) - 27 Jan 2010 Differences are minor, reloc of some fields | Adopt V1 (27 Jan) as master | Confirm strategy OK with NI. AGREED
4 | ROI Message Guides (10 docs) | V1 - dates from 21 Dec 2009 to 20 Jan 2010 | N/A | N/A | Adopt as-is | Update for changes arising from actions here
5 | Consolidated Documentation of ROI Impacts | V1 - 21 Jan 2010 | N/A | N/A | Adopt as-is | Determine source/content of V5 of these guides Update for changes arising from actions here
6 | NI Message Guides (10 docs) | N/A | N/A | V5 (2 docs at V5.1) Dates mostly at 28 Jan 2010 | Adopt as-is | Determine version of Msg, Defs and Codes used as basis for these. OK, was latest. Ensure 2 docs at V5.1 are used as masters Update for changes arising from actions above
7 | NI Change Note | N/A | N/A | V1 - 9 Mar 2010 | Adopt as-is | Determine version of Msg, Defs and Codes used as basis for these. OK, was latest. Update for changes arising from actions here
8 | Value List Compare (VLC) | N/A | V5 (431KB) | V3.1 (434 KB) - 9 Mar 2010 CDA say this is master | Combine VLC and Data Codes into single file VLC should be master, and will retain some clearly demarked "working" tabs At go live in both jurisdictions, remove "working" tabs from file | Confirm strategy is OK with NI. OK Combine Data Codes with VLC Update combined file for changes arising from actions here. AGREED

## HBL Business Changes
HRDS - Harmonisation Retail Design Services - HBL V2.1
Summary of Changes since HBL V2.0, their impacts and approval status |  |  |  |  | HBL Core Elements |  | HBL Derivative Elements
CR Name | Ver | Org. Jur. | Class- ification | Request Description | MM | Defs & Codes | ROI MM Guides | NI MM Guides | ROI Impact | HWG Position | Date of HWG | HSG Position
MCR 1053 | v3.0 | NI | Harmonisation | Fieldwork Cancellation on CoS (Partial Withdrawal) | No | Yes | No | Yes | Yes | Approved | 2011-08-10 | Approved
MCR 1070 | v2.0 | NI | Harmonisation | New Data Codes (Withdrawal) | No | Yes | No | Yes | Yes | Approved | 2011-08-10 | Approved
MCR 1090 | V2.0 | NI | Harmonisation | Updated Codes for 300 Series Market Messages | No | Yes | No | Yes | Yes | Approved | 2011-08-10 | Approved
MCR 1091 | V2.0 | NI | Harmonisation | Additional DUoS Tariff and Meter Configuration Codes | No | Yes | No | Yes | Yes | Approved | 2011-08-10 | Approved
CCR 005 | V1.0 | ROI | Harmonisation | New Meter Category Codes for Keypad Meters | No | Yes | No | No | Yes | Approved | 2011-08-10 | Approved

## HBL Corrections
HRDS - Harmonisation Retail Design Services
The following corrections were made to HBL V2.0 in response to inputs on that BaseLine from Market Patricipants and internal Q&A. As they reflect corrections to the previous HBL, they have not been brought back to the HWG for review but are included here as part of the current HBL V2.1.
1. HBL Definitions and Codes
Read Me First Tab
No changes
Data Items Tab
| Original HBL entry (with error highlighted) | [5 empty] | Correction and Rationale | Source of Correction | Correction Confimed by
| Business Name | Business Data Definition | Link to Values | Composition Instructions | Schema Name | Schema Enumerated?
| External ID | VARCHAR2 |  | AN (18) | 590 message, not on schema | N/A | Data Item removed from HBL as data item is not in Retail Schema. | HRDS QA | NIE/ESBN
| Total Quantities | This is the total consumption for the MPRN. |  | Num (15,3) | 590 message, not on schema | N/A | Data Item removed from HBL as data item is not in Retail Schema. | HRDS QA | NIE/ESBN
| Total Unit Rows | This is the total number of line items in the file i.e. excluding the header and footer lines. |  | Num (9) | 590 message, not on schema | N/A | Data Item removed from HBL as data item is not in Retail Schema. | HRDS QA | NIE/ESBN
| Tariff Configuration Code | A code to indicate the retail tariff required by the Supplier for a keypad metered Meter Point. | Values | AN (2) | TariffConfigurationCode | Yes | Schema Enumerated set to No. Original entry in error. | HRDS QA | NIE/ESBN
| Fax | This field is intended to store a Fax telephone number where applicable |  | AN (20) | Fax - Number | N/A | Schema name set to Number. Original entry in error. | HRDS QA | NIE/ESBN
| Fax Ext | This field is intended to store a Fax extension telephone number where applicable |  | AN (10) | Fax - Extn | N/A | Schema name set to Extn. Original entry in error. | HRDS QA | NIE/ESBN
| Phone Number 1 | This is the principal phone number of a contact and must be populated if the segment is provided and contact number is known by Sender. |  | AN (20) | PhoneOne - Number | N/A | Schema name set to Number. Original entry in error. | HRDS QA | NIE/ESBN
| Phone Number 2 | This field can be used for the secondary phone number where this is required. |  | AN (20) | PhoneTwo - Number | N/A | Schema name set to Number. Original entry in error. | HRDS QA | NIE/ESBN
| Phone Ext 1 | This is the principal phone number overflow field for storing number extensions where applicable |  | AN (10) | PhoneOne - Extn | N/A | Schema name set to Extn. Original entry in error. | HRDS QA | NIE/ESBN
| Phone Ext 2 | This is the secondary phone number overflow field for storing number extensions where applicable. |  | AN (10) | PhoneTwo - Extn | N/A | Schema name set to Extn. Original entry in error. | HRDS QA | NIE/ESBN
| Previous Supplier | The code identifying the previous Supplier of the customer. Used in Change of Tenancy History segement in 010 and in 140 - Change of Tenancy History. |  | AN (3) | PreviousSupplier | N/A | Schema Enumerated? Changed to No. Included link to Supplier ID values in Codes tab. | HRDS QA | NIE/ESBN
| Supplier MPID Old | A code identifying the Old Supplier to the new supplier in the confirmation of a Change of Supplier to support Debt management process in NI. |  | AN (3) | SupplierMPIDOld | N/A | Schema Enumerated? Changed to No. Included link to Supplier ID values in Codes tab. | HRDS QA | NIE/ESBN
| Meter Category | Meter Category is a code allocated by Meter Asset Manager to denote the manufacturer and type of meter. | Values | AN (5) | MeterCategoryCode | No | Composition Instructions set to AN(15). Originall setting of 5 was in error. | Supplier | NIE/ESBN
Data Codes Tab
| Original HBL entry (with error highlighted) | [5 empty] | Correction and Rationale | Source of Correction | Correction Confimed by
| Unique Ref | Data Item | Code Value | Code Value Description | Valid in ROI? | Valid in NI?
| 88 | Load Factor | LF1 | 0<30% | Yes | Yes | Valid in NI? is now set to "No" as this was initially set to "Yes" in error. | Supplier | CDA
| 88 | Load Factor | LF2 | 30% =<LF 2 <50% | Yes | Yes
| 88 | Load Factor | LF3 | >= 50% | Yes | Yes
| 89 | Load Factor New | LF1 | 0<30% | Yes | Yes
| 89 | Load Factor New | LF2 | 30% =<LF 2 <50% | Yes | Yes
| 89 | Load Factor New | LF3 | >= 50% | Yes | Yes
| 156 | Read Type | D | Deemed actual read | Yes | No | Line removed as code "D" is not valid in either jurisdiction and was left in the original HBL in error . | Supplier | ESBN
| 120 | No Read Code | 79 | Block Estimate - Planned | Yes | Yes | Valid in NI? Is now set to "No". These codes were to be used in NI as per DR1090 but this DR was corrected before approvel at the HWG of 10 Aug 2011. | CDA | CDA
| 120 | No Read Code | 80 | Block Estimate - Unplanned | Yes | Yes
| 131 | Outcome Reason | C001 | Completed as requested | Yes | Yes | Value not valid in ROI. Original entry in error. | HRDS QA | ESBN
| 131 | Outcome Reason | DN01 | D/E - At Cutout | Yes | No | Value not valid in ROI. Original entry in error. Removed from schema | Supplier | ESBN/NIE
| 131 | Outcome Reason | DN02 | D/E - Non Standard | Yes | No | Value not valid in ROI. Original entry in error. Removed from schema | Supplier | ESBN/NIE
| 131 | Outcome Reason | DS01 | D/E - At Cutout | Yes | No | Value not valid in ROI. Original entry in error. Removed from schema | HRDS QA | ESBN/NIE
| 131 | Outcome Reason | DS02 | D/E - Non Standard | Yes | No | Value not valid in ROI. Original entry in error. Removed from schema | HRDS QA | ESBN/NIE
| 131 | Outcome Reason | RE01 | Re-Energised | Yes | No | Value not valid in ROI. Original entry in error. Removed from schema | HRDS QA | ESBN/NIE
2. HBL Market Messages
| Read Me First Tab |  | Change Made
|  | Type | Clarified the meaning fo the possible values in this column on the Market Messages tab
|  | WS | Clarified the meaning of the possible values in this column on the Market Messages tab
|  | Value | Clarified the meaning of the possible values in this column on the Market Messages tab
|  | RoI Impact | Added important caveat around the historic nature of the contents of this column in the Market Messages tab
|  | NI Impact | Added important caveat around the historic nature of the contents of this column in the Market Messages tab
Market Messages Tab
| Original HBL entry (with error highlighted) | [9 empty] | Correction and Rationale | Source of Correction | Correction Confimed by
| Market Message | Segment | Seg Use | Data Item | Use | Chars | Type | WS | Pattern | Value
| 030 |  |  | AccessArrangements | opt | 100 | string | pre | yes | no | 030 replaced with 010. 030 was entered on 010 message in error. | HRDS QA | NIE
| 106E |  |  | CountyIreland | opt | 3 | string | pre | no | yes | Removed data items from message. Original inclusion was in error. | Supplier | NIE/ESBN
| 106E |  |  | Country | opt | 3 | string | pre | no | yes
| Data Items by MM List Tab |  | Change Made
|  | To be Removed in Harmonised Schema? | Added new functionality to allow filtering of Data Item list by inclusion or removal from Harmonised Schema