## HBL Strategy (hidden)
Harmonisation Baseline - Strategy for Update and Maintenance
Overall Strategy
1 | Refresh existing Baseline on which to lay down accumulated and emerging changes
Reconcile published and later versions of individual baseline elements and merge VLC & Data Codes
(See Strategy and approach below for each of the current baseline elements to address above issue)
Incorporate any omissions/errors in existing materials as they arise
Agree new baseline with all internals
2 | Apply accumulated changes since original baseline
See list from TO'N overleaf - appear to be mostly additions of codes and the like
Need quick survey to ensure comprehensiveness of this list
Agree new baseline with all internals
3 | Apply emerging Market Change related changes, both NI and ROI
See list overleaf - magnitude of changes varies; majority of NI-sourced changes may not be big hit on ROI elements
ROI-originated changes will be limited between now and golive
No. | Baseline Component | MCR1002 (ROI) - published 28 Jun 2010 | NI Email - 28 Jan 2010 | Other Sources (various dates) | Strategy | Actions Needed
1 | Market Messages (15 docs) | V3 Dates differ but are mostly 14 Dec 2009 (14 files). Files were delivered from NI team on 21 Jan | V5 Larger file sizes than V3 Differences appear to be mostly spelling corrections (14 files) | Technical V5 - 9 Mar 2010 (1 file) Note: No sign of any V4 files with CG or in RMDS inbox | Adopt V5 as master (incl. Technical) | Reconcile V3->V5 Determine correct version of 4 suspects (De-reg, FW Responses, Obj and Can, SONI) DONE - will take 28th Jan dated files in all cases
2 | Data Definitions | V1 (102 KB) Approx. 200 ROI defs and 20 NI defs. | V5 (217 KB) Differences are extra rows and columns | N/A | Adopt V5 as master | Confirm new strategy OK with NI. AGREED
3 | Data Codes | V1 (172 KB) Includes ALL coded fields, with special ref to ROI changes (5 cases) and new NI-derived codes (28 cases) | N/A (but see VLC below) | V1 (but at 178 KB) - 27 Jan 2010 Differences are minor, reloc of some fields | Adopt V1 (27 Jan) as master | Confirm strategy OK with NI. AGREED
4 | ROI Message Guides (10 docs) | V1 - dates from 21 Dec 2009 to 20 Jan 2010 | N/A | N/A | Adopt as-is | Update for changes arising from actions here
5 | Consolidated Documentation of ROI Impacts | V1 - 21 Jan 2010 | N/A | N/A | Adopt as-is | Determine source/content of V5 of these guides Update for changes arising from actions here
6 | NI Message Guides (10 docs) | N/A | N/A | V5 (2 docs at V5.1) Dates mostly at 28 Jan 2010 | Adopt as-is | Determine version of Msg, Defs and Codes used as basis for these. OK, was latest. Ensure 2 docs at V5.1 are used as masters Update for changes arising from actions above
7 | NI Change Note | N/A | N/A | V1 - 9 Mar 2010 | Adopt as-is | Determine version of Msg, Defs and Codes used as basis for these. OK, was latest. Update for changes arising from actions here
8 | Value List Compare (VLC) | N/A | V5 (431KB) | V3.1 (434 KB) - 9 Mar 2010 CDA say this is master | Combine VLC and Data Codes into single file VLC should be master, and will retain some clearly demarked "working" tabs At go live in both jurisdictions, remove "working" tabs from file | Confirm strategy is OK with NI. OK Combine Data Codes with VLC Update combined file for changes arising from actions here. AGREED

## HBL V2 Change History
HRDS - Harmonisation Retail Design Services
Summary of Changes since HBL V1.0, their impacts and approval status |  |  |  |  | HBL Elements Impacted
CR Name | Ver | Org. Jur. | Class- ification | Request Description | HBL Core (Def & Codes / MMs) | ROI MM Guides | NI MM Guides | Date Recomm- ended at HWG | HSG Position
MCR 177 | v2.0 | ROI | ROI-Specific | New DG4 Tariff for Local Authority Public Lighting | Yes | Yes | Yes | N/A | N/A
MCR 178 | v1.0 | ROI | Harmonisation | Treatment of Supplier Unit excess of Generation over Demand | No | Yes | Yes | N/A | N/A
MCR 180 | v1.0 | ROI | ROI-Specific | Sending of additional messages to EirGrid-TSO | No | Yes | No | N/A | N/A
CCR003 | v1.0 | ROI | ROI-Specific | Addition of New Unmetered Type (SONE, CDOT, MH) | Yes | Yes | No | N/A | N/A
CCR004 | v1.0 | ROI | ROI-Specific | Addition of New Unmetered Type (BUS3) | Yes | Yes | No | N/A | N/A
MCR 1003 | v2.0 | NI | Harmonisation | Addition of New Value Codes | Yes | No | No | 2010-10-26 | Approved
MCR 1004 | v2.0 | NI | Harmonisation | Supplier to use the MCC on 010 New Connection Registration Market Message as agreed by customer at the New Connection Application stage | No | No | Yes | 2010-10-26 | Approved
MCR 1009 | v2.0 | NI | Harmonisation | Removal of Cleansed Address Indicator | No | No | Yes | 2010-10-26 | Approved
MCR 1012 | v2.0 | NI | Harmonisation | Removal of 303R Market Message for Implausible Reads. Only use 303R Market Message to Reject Invalid Metering Read Details on Supplier Provided Reads | Yes | No | Yes | 2010-10-26 | Approved
MCR 1014 | v2.0 | NI | Harmonisation | Change the format of the DUoS and Transactional Supplier Invoices and MPRN level details | No | No | Yes | 2010-10-21 | Approved
MCR 1015 | v2.0 | NI | Harmonisation | Remove Field Name ''PostCodeMPA'' on Relevant Market Messages and Revert Back to the Original Field Name ''PostCode'' | Yes | Yes | Yes | 2010-10-26 | Approved
MCR 1018 | v2.0 | NI | Harmonisation | To Allow Supplier Provided Readings received after 12 months to be validated in the same way as any other reading | No | No | Yes | 2010-10-21 | Approved
MCR 1024 | v2.2 | ROI | Harmonisation | Global Aggregation | Yes | Yes | Yes | 2011-02-23 | Approved
MCR 1028 | v2.0 | ROI | Harmonisation | Submission of multiple Customer Service Codes on 010, 013, 016 and 017 MMs | Yes | Yes | Yes | 2010-12-01 | Approved
MCR 1030 | v3.0 | NI | Harmonisation | Read Single Rate Keypad Meters | No | No | Yes | 2010-12-15 | Approved
MCR 1031 | v3.0 | NI | Harmonisation | Change to COS Registration for Keypad | No | No | Yes | 2010-12-23 | Approved
MCR 1032 | v2.0 | NI | Harmonisation | Alignment of Meter Configuration Codes | Yes | Yes | Yes | 2010-11-18 | Approved
MCR 1037 | v5.0 | ROI | Harmonisation | WP 18 Procedure where a customer has a Budget Controller (Token Meter) Installed | No | Yes | No | 2010-11-18 | Approved
MCR 1038 | v2.0 | NI | Harmonisation | Supplier Advice of Long-Term Vacant Property | Yes | Yes | Yes | 2010-12-01 | Approved
MCR 1040 | v2.0 | ROI | Harmonisation | New Value in 591 message for Unmetered Total Usage Factor | Yes | Yes | Yes | 2010-12-01 | Approved
MCR 1041 | v3.0 | NI | Harmonisation | Registration Cancellation Timescale | No | No | Yes | 2010-12-01 | Approved
MCR 1042 | v3.0 | NI | Harmonisation | Removal of non-visit keypad meter configuration changes | Yes | Yes | Yes | 2011-02-23 | Approved
MCR 1044 | v2.0 | NI | Harmonisation | Removal of Cooling off Period | No | No | Yes | 2010-12-16 | Approved
MCR 1051 | v2.0 | NI | Harmonisation | New 017 Meter Point Status Reason - Re-energise (Rewire) | Yes | No | Yes | 2011-04-06 | Approved
MCR 1052 | v2.0 | NI | Harmonisation | Removal of Old Keypad Premises Number from Market Messages | Yes | Yes | Yes | 2011-04-06 | Approved
MCR 1053 | v2.0 | NI | Harmonisation | Fieldwork Cancellation on CoS | Yes | No | Yes | 2011-04-06 | Approved
MCR 1054 | v2.0 | NI | Harmonisation | Removal of Supplier Certification | Yes | No | Yes | 2011-04-06 | Approved
MCR 1055 | v2.0 | NI | Harmonisation | New Register Types, Time of Use Codes and MCC Codes | Yes | No | Yes | 2011-05-18 | Approved
MCR 1057 | v2.0 | NI | Harmonisation | Removal of Usage Type on 010 | Yes | Yes | Yes | 2011-05-18 | Approved
MCR 1058 | v2.0 | NI | Harmonisation | Meter Works Type Code, Access Arrangements - CoS | Yes | Yes | Yes | 2011-04-06 | Approved
MCR 1062 | v2.0 | NI | Harmonisation | Removal of DUoS Tariff - T051 | Yes | No | No | 2011-05-18 | Approved
MCR 1068 | v2.0 | NI | Harmonisation | New MESN Code | Yes | No | Yes | 2011-05-18 | Approved
MCR 1070 | v2.0 | NI | Harmonisation | New Data Codes | Yes | No | Yes | 2011-05-18 | Approved
MCR 1073 | v2.0 | NI | Harmonisation | Supplier Advice of Long Term Vacant Property | Yes | Yes | Yes | 2011-05-18 | Approved
MCR 1077 | v1.0 | NI | Harmonisation | NI Enduring Solution - sundry updates | Yes | Yes | Yes | 2011-06-15 | Approved
MCR 1081 | v1.0 | NI | Harmonisation | Harmonised Data Items Work Type and Unmetered Type | Yes | No | Yes | 2011-06-29 | Approved
MCR 1082 | v1.0 | NI | Harmonisation | New "Chargeable Service Capacity 5 Year Agreement End Date" field on 301 | Yes | Yes | Yes | 2011-06-29 | Approved