## Sheet1
Task Name | Start | Finish | Resource | Area | Status
Planning
Publish Overall Retail Market IPT Plan on RMDS website | Fri 18/11/2022 | Fri 18/11/2022 | RMDS | IPT | Scheduled
IPT Test Collateral and Tool Preparation
IPT volunteers to confirm contact details to RMDS | Fri 18/11/2022 | Tue 22/11/2022 | MPs | IPT | Scheduled
RMDS confirms IPT participants | Wed 23/11/2022 | Wed 23/11/2022 | RMDS, MPs | IPT | Scheduled
Circulate V1.0 of IPT workbook to IPT Participants | Wed 30/11/2022 | Wed 30/11/2022 | RMDS | IPT | Scheduled
Allow one week for IPT Participant review | Wed 30/11/2022 | Tue 06/12/2022 | MPs | IPT | Scheduled
RMDS grants IPT Participants access to Evidence Storage Area. IPT Participants confirm access to Evidence Storage Area | Wed 23/11/2022 | Wed 30/11/2022 | RMDS, MPs | IPT | Scheduled
Circulate V2.0 of IPT workbook to IPT Participants (including test data and Test Extranet access details) | Tue 06/12/2022 | Tue 06/12/2022 | RMDS | IPT | Scheduled
2 week Market Participant Data Prep Window | Tue 06/12/2022 | Fri 23/12/2022 | MPs | IPT | Scheduled
Connectivity to be verified as part of Cutover Dress Rehearsal window as communicated by RMDS on 18th Nov 2022 (Task for all MPs) | Mon 12/12/2022 | Fri 16/12/2022 | MPs, Market Message Hub Support Team | IPT | Scheduled
Send IPT Entry Criteria Checklist for IPT Participants | Mon 19/12/2022 | Mon 19/12/2022 | RMDS | IPT | Scheduled
IPT Participants to send test market message to prove end to end connectivity in advance of IPT start. Details to be included in the IPT Entry Criteria Checklist. | Tue 03/01/2023 | Fri 06/01/2023 | MPs | IPT | Scheduled
Receive confirmation from MPs that Checklist is completed | Tue 03/01/2023 | Fri 06/01/2023 | MPs | IPT | Scheduled
IPT Execution Window | Mon 09/01/2023 | Fri 27/01/2023 | RMDS, Assurance Body, ESBN, MPs, Market Message Hub Support Team | IPT | Scheduled
IPT Test Execution | Mon 09/01/2023 | Fri 27/01/2023 | MPs | IPT | Scheduled
Issue IPT Exit Report to CRU | Mon 30/01/2023 | Tue 31/01/2023 | Assurance Body | IPT | Scheduled