## Market Plan
Area | Task | Start | Finish
Planning | Market Participants to advise RMDS of project technical contacts | 27th April 2022 | 27th April 2022
Planning | High Level Market Plan issued to Market Participants | 27th May 2022 | 27th May 2022
Assurance | Assurance Approach approved by CRU | 6th June 2022 | 17th June 2022
Assurance | Assurance Approach issued to Market Participants | 20th June 2022 | 20th June 2022
Planning | Project to be in contact with Technical Reps on IP and Firewall Rules | 15th August 2022 | 15th August 2022
Planning | Window for Market Participants to have Firewall rules in place for TEST EMMAs only | 12th Sep. 2022 | 10th Oct. 2022
Planning | Connectivity checks on ROI TEST EMMAs | 25th Nov. 2022 | 8th Dec. 2022
Assurance | Self-Assessment Participant Questionnaire issued | 29th Aug. 2022 | 29th Aug. 2022
Assurance | Return completed Participant Questionnaires to RMDS | 31st Aug. 2022 | 20th Sep. 2022
Assurance | Assurance Body issue Self-Assessment Report to CRU | 21st Sep. 2022 | 27th Sep. 2022
Assurance | ESB Networks Project Formal Assessment | 10th Oct. 2022 | 14th Oct. 2022
Assurance | Assurance Body issue Formal Assessment Report to CRU | 17th Oct. 2022 | 4th Nov. 2022
Planning | IPT Plan made available via RMDS | 18th Nov. 2022 | 18th Nov. 2022
Cutover | High Level Cutover Approach communicated to Market Participants | 30th Nov. 2022 | 30th Nov. 2022
Assurance | IPT Preparation - 2 week window to prep test cases | 6th Dec. 2022 | 23rd Dec. 2022
Assurance | IPT Execution Window | 9th Jan. 2023 | 27th Jan. 2023
Planning | Deadline for Market Participants to have Firewall rules in place for PROD EMMAs | 16th Jan. 2023 | 27th Jan. 2023
Planning | Connectivity checks on ROI PROD EMMAs | 30th Jan. 2023 | 8th Feb. 2023
Cutover | Detailed Cutover Plan issued to Market Participants | 2nd Feb. 2023 | 2nd Feb. 2023
Assurance | IPT Report issued to CRU | 30th Jan. 2023 | 31st Jan. 2023
Assurance | Final Assurance Report issued to CRU | 1st Feb. 2023 | 1st Feb. 2023
Cutover | Hypercare Approach issued to Market Participants | 6th Feb. 2023 | 6th Feb. 2023
Assurance | CRU assessment of Final Exit Report | 2nd Feb. 2023 | 9th Feb. 2023
Assurance | CRU final engagement - 'Go/No Go Decision' | 9th Feb. 2023 | 9th Feb. 2023
Cutover | Execute Cutover | 10th Feb. 2023 | 12th Feb. 2023
Cutover | Hypercare Window | 13th Feb. 2023 | 10th Mar. 2023