## Market Cutover Plan
HUB Relocation Cutover Plan
No | KEY MARKETS TASKS | START | FINISH | Status | RESPONSIBLE
Preparation
1 | RMDS to request a Business and Technical contact from each Market Participant (MP) for cutover activities. | 2023-01-20 | 2023-02-01 | Complete | RMDS
2 | MPs to confirm their contact(s) for cutover activities to RMDS - each MP must provide a Technical and Business contact for the cutover activities. | 2023-01-23 | 2023-01-27 | Complete | MPs
3 | Deadline for MPs to have firewall rules in place for production EMMAs | 2023-01-16 | 2023-01-27 | Complete | MPs
4 | Connectivity Checks to/from ROI Production EMMAs to new ROI Hub in advance of cutover | 2023-01-30 | 2023-02-08 | In-Progress | Project Team, (Access by MP's)
5 | MPs to complete Market Message (MM) reconciliation on a daily basis up to cutover (602 MM) | 2023-02-02 | 2023-02-10 | In-Progress | MPs
6 | Mandatory confirmation of completed reconciliations required via email (602 MM) from MPs to RMDS | 2023-02-10 10:00 | 2023-02-10 10:00 | To Do | MPs
7 | Reminder email sent to all MPs from RMDS to stop sending MMs at 18:00 on Friday 10th February. Please ensure EMMA is left in normal operational mode for the weekend. | 2023-02-10 10:00 | 2023-02-10 10:00 | To Do | RMDS
Cutover Weekend
8 | MPs to stop sending MMs from this point. No further MMs until confirmation of resumption of services. MPs may continue to receive messages from ESBN until 20:00 on the 10/02/2023. | 2023-02-10 18:00 | 2023-02-11 18:00 | To Do | MPs
9 | Hub Relocation preparation activities. | 2023-02-10 18:00 | 2023-02-11 08:00 | To Do | Project Team
10 | 602MM issued to MPs up to the point of Hub Shutdown for post-cutover reconciliation purposes. | 2023-02-10 19:30 | 2023-02-10 20:00 | To Do | Project Team
11 | Hub Relocation Project Activities. | 2023-02-11 08:00 | 2023-02-11 10:00 | To Do | Project Team
12 | ESBN Testing commences. | 2023-02-11 10:00 | 2023-02-11 11:00 | To Do | Project Team
13 | Notification Email: Milestone 1 - ESBN Testing Complete (Point of no Return) | 2023-02-11 11:00 | 2023-02-11 11:00 | To Do | RMDS
14 | MP's EMMAs connected to Hub in ROI. Note: Group times are approximate, MP's cutover contacts should be available in the window and until the EMMA is connected to the Hub in ROI. Refer to RMDS communication on 03/02/2023 for your group no. | 2023-02-11 11:00 | 2023-02-11 16:30 | To Do | Project Team
15 | Group 1 | 2023-02-11 11:00 | 2023-02-11 12:15 | To Do | Project Team
16 | Group 2 | 2023-02-11 12:15 | 2023-02-11 13:30 | To Do | Project Team
17 | Group 3 | 2023-02-11 14:00 | 2023-02-11 15:15 | To Do | Project Team
18 | Group 4 | 2023-02-11 15:15 | 2023-02-11 16:30 | To Do | Project Team
19 | Final ESBN checks prior to resumption of services | 2023-02-11 17:00 | 2023-02-11 18:00 | To Do | Project Team
20 | Notification Email: Milestone 2 - Cutover is complete. Resumption of normal services. | 2023-02-11 18:00 | 2023-02-11 18:00 | To Do | RMDS
21 | Note: Sunday 12th February is retained as a contingency day if additional work is required on the new ROI Hub. The Milestone 2 email may issue on the 12th February if this contingency day is required. | 2023-02-12 08:00 | 2023-02-12 18:00 | To Do | Project Team
22 | Hypercare - MPs contact RetailMarketHubSupport (ESB Networks) <RetailMarketHubSupport@esb.ie> if they encounter TIBCO related issues. Conference Call will be scheduled for 15:00 on Monday 13th February. Hypercare plan will be issued 7th February. | 2023-02-13 08:30 | 2023-03-10 17:00 | To Do | Project Team

## Milestone Calls (hidden)
Milestone Calls
Conf Call details
Estimated
Call No | Checkpoint | Date | Start | End | Notes | Attendees
1 | Milestone 1: Commence Cutover (Friday) | 10.2.2023 | 5:00PM | 5:10PM |  | Project Team/ESB
2 | Milestone 2 - Call to restart cutover (Saturday) | 11.2.2023 | 11.00am | 11.10am | Report status of EI EMMA Heartbeats Decision based on this: 1. Procced 2. Delay 1 hour and continue to monitor heartbeats 3. Rollback | Project Team/ESB
3 | Milestone 3 - Point of No return |  | 1.00pm | 1.10pm | Report outcome of SAP PO repointing Decision based on this 1. Procced 2. Delay 1 hour and continue to fix SAP PI repointing issue/s 3. Rollback | Project Team/ESB
4 | Milestone 3 - EI Message Check - Call to proceed |  | 2.00pm | 2.10pm | Report outcome of MP Testing Decision based on this 1. Procced 2. Delay 1 hour and continue with MP testing 3. Rollback | Project Team/ESB
5 | Milestone 4 - Remaining MPs Message Check - Call to proceed The time of this call will be dependent on the number of Suppliers who opt in. 10.00pm is worse case |  | 10.00pm | 10.10pm | Report outcome of MP Connectivity all MP Testing MP Decision based on this 1. Procced 2. Delay 1 hour and continue with MP testing 3. Fix Forward (Sunday 12/2) 4. Rollback (Sunday 12/2) | Project Team/ESB
Note on F10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Deally. David (ESB Networks) lets agree the criteria here for MP's connected and circumstance where we would proceed, delay, defer to Sunday or Rollback

## Data (hidden)
Task Type
Action
Comms
Decision Point
Information
Milestone
Primary - Team List | [6 empty] | Secondary - Team List
Name | Role | Company | Location | Telephone 1 | Telephone 2 | Email | Name | Location | Telephone 1 | Telephone 2 | Email
Aidan McCrossan | TIBCO Architect | Atos | Mossley Mill | +44 (0)7970 112551 |  | aidan.mccrossan@atos.net
Angela Grace | ESB ISC Support Lead | ESBN | Home Based | +353 87 6679236 |  | angela.grace@esb.ie
Billy Crowley | ESBN Technical | ESBN | Home Based | +353 87 2029049 |  | billy.crowley@esb.ie
Brendan Philbin | Co-ordinator | ESBN | Home Based | +353 85 725 3817 |  | Brendan.philbin@esb.ie | Declan Higgins
Carl Murphy | ESBN Business | ESBN | Home Based | + 353879455396 |  | carl.murphy@esb.ie
Chethan K N | TIBCO Developer | Atos | Atos - India | +91 9844 907855 |  | chethan.2.kn@atos.net
Satish Bande | TIBCO Developer | Atos | Atos - India | +44 7459 467182 |  | venkata.bande@atos.net
Rajkiran S | TIBCO Developer | Atos | Atos - India |  |  | rajkiran.s@atos.net
Dalip Singh | DB2 DBA | Atos | Atos - India | +919019698825 |  | dalip.singh@atos.net
David Deally | ESBN Business | ESBN | Home Based | +353 86 170 2356 |  | david.bradley2@esb.ie
David Deally | ESBN Business | ESBN | Home Based | 353 87 281 6271 |  | david.deally2@esb.ie
Jan Knop | OSG | ESBN | Home Based | Personal mobile |  | Jan.knop@esb.ie
John Bracken | ESBN Technical | ESBN | Home Based | +353 87 64 69 070 |  | John.Bracken@esb.ie
Lorna Davey | ESBN Cutover Manager | ESBN | Home Based | +353 87 283 6683 |  | lorna.davey@esb.ie
Mark Nixon | NIEN IT | NIEN | Home Based | +44 (0)7342 052978 |  | mark.nixon@nienetworks.co.uk
Meyrick Owsley | NIEN Cutover Manager | Atos | Home Based | +44 (0) 7841 568850 |  | meyrick.owsley@atos.net
Patrick Moran | Supplier Management | ReMCoDs | Home Based | (+353) 87 9794704 |  | patrick.moran2@esb.ie
Stuart Graham | NIEN Programme Manager | NIEN | Home Based | +44 (0)7880 052964 |  | stuart.graham3@nienetworks.co.uk
Sanket Joshi | TIBCO Developer | Atos | Mossley Mill | +91-9881255486 |  | sanket.joshi@atos.net
Eoin O'Flagherty | SAP PO | ESBN | Home Based
Task Status
Not Started
In-Progress
Completed
Comms
Group A
Group A, B
Group A, C
Group B
Group B, C
Group C
Individual