## Sheet1
Area | Task | Start | Finish
Planning | Market Plan Published | 2022-03-16 | 2022-03-16
Design | Updated MCR1213 | 2022-03-16 | 2022-03-16
Assurance | Assurance Approach circulated to Market Participants | 2022-03-25 | 2022-03-25
Assurance | Assurance Approach agreed at IGG | 2022-03-30 | 2022-03-30
Assurance | Self Assessment Participant Questionnaire Issued to Market Participants | 2022-03-30 | 2022-03-30
Assurance | Market Participants return completed Participant Questionnaires | 2022-03-30 | 2022-04-13
Design | Publication of file structure definition. 344 xml file and 345 xml file | 2022-03-31 | 2022-03-31
Design | Publication of file structure definition. New Webservice Metadata file | 2022-03-31 | 2022-03-31
Design | Publication of file structure definition. DOM_CUST file | 2022-03-31 | 2022-03-31
Design | Draft Market Design Documentation published | 2022-04-14 | 2022-04-14
Design | Screenshot of Extranet change and confirmation of field definition | 2022-04-22 | 2022-04-22
Assurance | ESBN Formal Assessment (one day site visit) | 2022-04-25 | 2022-05-06
Assurance | Gemserv issue Self Assessment Report to CRU | 2022-04-27 | 2022-04-27
Assurance | IPT Plan made available to Market Participants | 2022-05-06 | 2022-05-06
Assurance | Market Participants indicate willing to participate in IPT | 2022-05-06 | 2022-05-13
Design | Publication of file structure definition. 344 xml file and 345 xml file (sample files) | 2022-05-09 | 2022-05-09
Design | Publication of file structure definition. New Webservice Metadata file (sample file) | 2022-05-09 | 2022-05-09
Design | Publication of file structure definition. DOM_CUST file (sample file) | 2022-05-09 | 2022-05-09
Assurance | Gemserv issues Formal Assessment Report to CRU | 2022-05-13 | 2022-05-13
Assurance | IPT Prep Window | 2022-05-16 | 2022-05-27
Cutover | Cutover Approach published | 2022-05-17 | 2022-05-17
Assurance | IPT Execution Window | 2022-05-30 | 2022-06-10
Assurance | IPT Exit Report issued to CRU | 2022-06-14 | 2022-06-14
HyperCare | HyperCare approach published | 2022-06-20 | 2022-06-20
Cutover | CRU Go/No Go decision | 2022-06-21 | 2022-06-21
Cutover | Cutover Execution | 2022-06-28 | 2022-06-28
Cutover | Go Live | 2022-06-28 | 2022-06-28
Design | Final Market Design Documentation Published (MMR) | 2022-06-29 | 2022-06-29
HyperCare | HyperCare | 2022-06-29 | 2022-07-27