## Sheet1
MCR1213 Interim Retail Market Microgeneration Solution Cutover Execution Plan
ID | Key Market Task | Start Date | Finish Date | Details
Pre-Cutover Activities
1 | Provision of global list of MPRNs with an MEC by ESB Networks to suppliers | 20.06.2022 | 20.06.2022
2 | Suppliers confirm SFTS access for 'Microgen' folder | 21.06.2022 | 23.06.2022 | Suppliers should confirm access to RMDS between 21.06.2022 - 23.06.2022. Suppliers will be granted access to 'Microgen' folder on 21.06.2022 in SFTS using existing supplier login credentials utilised for Downloadable Files. No new user accounts will be required for Go-Live. Suppliers have the option to update their login credentials via RMDS post Go-Live.
Cutover Activities
3 | 301MM (with MEC rounding update) | 22.06.2022 | 22.06.2022 | The MEC value on the 301MM will be correctly rounded from this point onwards.
4 | Webservice updates | 28.06.2022 | 28.06.2022 | The changes to the Webservice will be applied between (9.00 - 11.00). During this time the Webservice will still be available but there may be varying levels of response whilst changes are being made.
5 | Extranet updates | 28.06.2022 | 28.06.2022 | The changes to the Extranet will be applied between (9.00 - 14.00). During this time the Extranet will still be available but there may be varying levels of response whilst changes are being made.
6 | 344 xml and 345 xml files (including backdated data) | 28.06.2022 | 28.06.2022 | 344 xml and 345 xml files will be available via SFTS by 14.00. Suppliers are reminded that files are deleted from the SFTS after 30 days.
7 | ESB Networks to issue communication via RMDS when above Cutover activities are complete | 28.06.2022 | 28.06.2022
8 | DOMS_CUST and COMM_CUST files with MEC updates | 02.07.2022 | 02.07.2022 | DOMS_CUST and COMM_CUST files will become visible to suppliers in-line with existing timelines
Additional points to note
1 | ESBN will take a fix and go forward approach for any issues encountered after changes are deployed to production systems
2 | Market Participants will be contacted by MRSO in Q4 2022 regarding their preferred supplier unit to be used for microgeneration export quantities and this task is not considered as part of the cutover