## Sheet1
Task Name | Start | Finish | Resource | Area | Status
Planning
Publish Overall Retail Market IPT Plan on RMDS website | Fri 06/05/2022 | Fri 06/05/2022 | RMDS | IPT | Scheduled
IPT Test Collateral and Tool Preparation
IPT Prep Window | Fri 16/05/2022 | Fri 27/05/2022 | RMDS, MPs,Gemserv | IPT | Scheduled
Circulate Market Participant IPT workbook (including test data) | Fri 20/05/2022 | Fri 20/05/2022 | RMDS | IPT | Scheduled
Send IPT Entry Criteria Checklist for MPs | Mon 23/05/2022 | Mon 23/05/2022 | RMDS | IPT | Scheduled
Receive confirmation from MPs that Checklist is completed | Tue 24/05/2022 | Tue 24/05/2022 | RMDS, MPs | IPT | Scheduled
IPT Execution
IPT Execution Window | Mon 30/05/2022 | Fri 10/06/2022 | All | IPT | Scheduled
Assurance Final Outcome Report Phase | Tue 14/06/2022 | Tue 14/06/2022 | Gemserv, CRU | IPT | Scheduled
Go/No Go Decision | Tue 21/06/2022 | Tue 21/06/2022 | CRU | IPT | Scheduled