## Market Plan
Area | Jurisdiction | Task | Start | Finish
Planning | Both | Market Participants to advise ReMCoDS of technical contacts | 2021-02-23 | 2021-02-23
Planning | Both | High Level Market Plan issued to Market Participants | 2021-02-24 | 2021-02-24
Design | NI | EMMA Technical Specification issued to NI (Dual Suppliers) | 2021-02-26 | 2021-02-26
Planning | Both | Technical Questionnaire issued to Market Participants | 2021-02-26 | 2021-02-26
Design | Both | Webforms Look and Feel Overview issued to Market Participants | 2021-03-05 | 2021-03-05
Assurance | Both | Assurance Approach approved by RAs | 2021-04-09 | 2021-04-09
Assurance | Both | Assurance Approach issued to Market Participants | 2021-04-12 | 2021-04-12
Planning | NI | Deadline for Market Participants to have new NI EMMA infrastructure ready (To Be NI Production & NI Test) |  | 2021-04-30
Planning | ROI | Market Participant's existing ROI Test EMMA Upgrades (some EMMA upgrades will be deferred until IPT Execution window) | 2021-04-29 | 2021-06-29
Planning | NI | Market Participant's existing NI Test EMMA Upgrades (2 NI Only Suppliers) | 2021-04-29 | 2021-06-29
Planning | NI | Market Participant's new NI Test EMMA Builds | 2021-05-05 | 2021-06-28
Assurance | Both | Self-Assessment Participant Questionnaire issued | 2021-05-07 | 2021-05-07
Assurance | Both | Return completed Participant Questionnaires to ReMCoDS | 2021-05-28 | 2021-05-28
Assurance | Both | Assurance Bodies issue Self-Assessment Report to RAs | 2021-06-11 | 2021-06-11
Assurance | Both | IPT Plan made available | 2021-06-21 | 2021-06-21
Cutover | Both | High Level Cutover Approach issued to Market Participants | 2021-06-25 | 2021-06-25
Planning | NI | Market Participant's new NI Production EMMA Builds | 2021-06-28 | 2021-08-17
Assurance | Both | ESB Networks and NIE Networks Project Formal Assessment | 2021-07-05 | 2021-07-16
Design | Both | Updated Webforms Guide issued to Market Participants | 2021-07-14 | 2021-07-14
Assurance | Both | Assurance Bodies issue Formal Assessment Report to RAs | 2021-07-23 | 2021-07-23
Assurance | Both | IPT Execution Window | 2021-08-09 | 2021-08-27
Cutover | Both | Detailed Cutover Plan issued to Market Participants | 2021-09-03 | 2021-09-03
Assurance | Both | IPT and Final Exit Report issued to RAs | 2021-09-10 | 2021-09-10
Cutover | Both | Hypercare Approach issued to Market Participants | 2021-09-15 | 2021-09-15
Assurance | Both | CRU and UR final engagement | 2021-09-17 | 2021-09-17
Cutover | Both | Execute Cutover | 2021-09-25 | 2021-09-26
Cutover | Both | Hypercare Window | 2021-09-26 | 2021-11-04
Cutover | ROI | Market Participant's ROI Production EMMA Upgrades | 2021-09-30 | 2021-10-22