## Sheet1
System Separation NI IPT Plan
Task Name | Start | Finish | Resource | Area | Status
Planning
Publish Overall Retail Market IPT Plan on RMDS website | Mon 21/06/21 | Mon 21/06/21 | ReMCoDS | IPT | Scheduled
IPT Test Collateral and Tool Preparation
Circulate NI Market Participant IPT workbook | Wed 14/07/21 | Wed 14/07/21 | CDA, MEPCT | IPT | Scheduled
2 week Market Participant Data Prep Window | Mon 26/07/21 | Mon 09/08/21 | MPs | IPT | Scheduled
ReMCoDS to inform MPs when the NI IPT environment is available | Tue 03/08/21 | Tue 03/08/21 | ReMCoDS | IPT | Scheduled
Receive confirmation from MPs that IPT systems successfully connected | Tue 03/08/21 | Fri 06/08/21 | CDA, MPs, Atos | IPT | Scheduled
IPT Execution | Mon 09/08/21 | Fri 27/08/21 | CDA, Neueda, NIE Networks, MPs, Atos | IPT | Scheduled
Issue final assurance outcome report to UR | Fri 10/09/21 | Fri 10/09/21 | MEPCT | IPT | Scheduled
Note: It is anticpated that an IPT workshop will be scheduled week commencing 26/07/21. Date to be confirmed