## Sheet1
Task Name | Start | Finish | Resource | Area | Status
Planning
Publish Overall Retail Market IPT Plan on RMDS website | Mon 21/06/21 | Mon 21/06/21 | RMDS | IPT | Complete
IPT Test Collateral and Tool Preparation
RMDS confirms IPT participants | Fri 25/06/21 | Fri 25/06/21 | RMDS, MPs | IPT | Complete
Circulate V1.0 of Market Participant IPT workbook | Mon 28/06/21 | Mon 28/06/21 | RMDS | IPT | Complete
Allow one week for MP review | Mon 28/06/21 | Mon 05/07/21 | RMDS, MPs | IPT | Complete
Circulate V2.0 of Market Participant IPT workbook | Mon 05/07/21 | Mon 05/07/21 | RMDS | IPT | Complete
Circulate V2.1 of Market Participant IPT workbook | Thu 15/07/21 | Thu 15/07/21 | RMDS | IPT | Scheduled
RMDS grants MPs access to Evidence Storage Area. MPs confirm access to Evidence Storage Area | Mon 19/07/21 | Mon 26/07/21 | RMDS, MPs | IPT | Scheduled
Circulate V3.0 of Market Participant IPT workbook (including test data) | Mon 26/07/21 | Mon 26/07/21 | RMDS | IPT | Scheduled
2 week Market Participant Data Prep Window | Mon 26/07/21 | Mon 09/08/21 | MPs | IPT | Scheduled
New Webforms installation package & installation instructions to be issued to MPs | Fri 06/08/21 | Fri 06/08/21 | RMDS | IPT | Scheduled
RMDS to inform MPs when the IPT environment is available (Test Extranet access details will be communicated by RMDS) | Fri 06/08/21 | Fri 06/08/21 | RMDS | IPT | Scheduled
Send IPT Entry Criteria Checklist for MPs | Fri 06/08/21 | Fri 06/08/21 | RMDS | IPT | Scheduled
Receive confirmation from MPs that Checklist is completed | Mon 09/08/21 | Fri 13/08/21 | RMDS, MPs | IPT | Scheduled
IPT Execution Window | Mon 09/08/21 | Fri 27/08/21 | RMDS, Gemserv, ESBN, MPs, Atos | IPT | Scheduled
MPs to install and activate new Webforms on Test EMMA as per instructions | Mon 09/08/21 | Thu 12/08/21 | MPs | IPT | Scheduled
IPT Test Execution | Mon 16/08/21 | Fri 27/08/21 | MPs | IPT | Scheduled
Issue final assurance outcome report to CRU | Fri 10/09/21 | Fri 10/09/21 | Gemserv | IPT | Scheduled