## Sheet1 (hidden)
TIBCO Hub Upgrade Schedule
No | KEY MARKETS TASKS | START | FINISH | RESPONSIBLE
Preparation
1 | MPs to complete MM reconciliation on a daily basis up to cutover |  |  | MPs
2 | ReMCoDS request a business and techincal contact from each Market Participant for cutover weekend. Contacts need to be available between 12:00 - 18:00 05.10.2019 and 09:00 to 18:00 on 06.10.2019. This is a precautionary measure and will only be required in the event of a connectivity issue with your EMMA. Once the cutover is complete an email will be issued which will relieve....exception: if you have confirmed that you wish to take part in the additional optional connectivity checks. | 2019-09-13 | 2019-09-13 | ReMCoDS
3 | ReMCoDS to contact Market Participants to see if they wish to take part in additional connectivity testing on the cutover. | 2019-09-13 | 2019-09-13 | ReMCoDS
4 | MPs confirm MP contacts for cutover weekend to ReMCoDS - each Market Participant must provide a technical and business contact for the cutover weekend. | 2019-09-20 | 2019-09-20 | MPs
5 | Market Participants to confirm if they wish to take part in the additional connectivity testing on the cutover. | 2019-09-20 | 2019-09-20 | MPs
6 | ReMCoDS to provide an optional connectivity testing window to each of the requesting MPs. 14:30 - 18:00. | 2019-09-25 | 2019-09-25 | ReMCoDS
7 | MPs who opt in for additional optional connectivity testing confirm availability for slot. MPs do not send messages until instructed to do so by ReMCoDS | 2019-09-27 | 2019-09-27 | MPs
8 | Reminder to all MPs to stop sending Market Messages 07:00 hrs on Saturday 05.10.2019. No further MMs until confirmation of resumption of Services | 2019-10-02 | 2019-10-02 | ReMCoDS
Execution Starts
10 | MPs to stop sending messages from this point (07:00 05.10.2019) | 2019-10-05 07:00 | 2019-10-05 07:00 | MPs
11 | 602 Reconcilation issued to all Market Participants MPs are not requested to reconcile at this time | 2019-10-05 09:00 | 2019-10-05 09:00 | Atos
12 | Upgrade Starts | 2019-10-05 09:15 | 2019-10-05 09:15 | Atos
13 | Upgrade complete - (internal note: this should be the time before EI and PNI connectivity testing commences) | Paul to enter new times | Paul to enter new times | Atos
14 | Milestone 1: Notification Email: Upgrade complete | Paul to enter new times | Paul to enter new times | ReMCoDS
15 | Network Operator Testing - (internal note: this should be the time for EI and PNI connectivity testing) | Paul to enter new times | Paul to enter new times | Atos
16 | Milestone 2: Network Operator Testing Complete (Point of no Return) | Paul to enter new times | Paul to enter new times | ReMCoDS
17 | Optional Connectivity Window 14:30 to 18:00 | Paul to enter new times | Paul to enter new times | MPs
18 | Milestone 3: Notification that cutover is complete. Resumption of normal services | Paul to enter new times | Paul to enter new times | Atos
19 | Hypercare - MPs contact ReMCoDS if they encounter TIBCO related issues. Conference Call will be scheduled for Monday 15:00 (07.10.2019) | 2019-10-07 | 2019-10-11 | ReMCoDS
EMMA Upgrade Schedule
No | KEY MARKETS TASKS | START | FINISH | RESPONSIBLE
1 | Market Participants confirm their availability for the agreed EMMA upgrade slot. | Complete
2 | ReMCoDS request business and technical contact for Production EMMA Upgrade (these contact may also be used for the IPT EMMAs. Atos will contact MPs directly regarding suitable times for IPT EMMA Upgrades. | 2019-09-13 | 2019-09-13
3 | Market Participants confirm business and technical contact for EMMA Upgrade | 2019-09-20 | 2019-09-20
4 | ReMCoDS provide technical instructions on how to download upgrade software on behalf of Atos to the MPs | 2019-09-24 | 2019-09-24
5 | MPs confirm that software is downloaded and appropriate access and permission levels are in place. | ?? | ??
6 | Atos will contact MPs directly on the day of their scheduled upgrade slot. | ?? | ??
7 | Atos upgrade EMMA and confirm to MP and ReMCoDS that upgrade is complete. | ?? | ??
8 | ReMCoDS send a notification to the Market once all Production EMMAs have completed. | ?? | ??
9
10

## Cutover Plan
System Separation, TIBCO Upgrade and Webforms Replacement Cutover Plan
Preparation
No | KEY MARKET TASKS | START | FINISH | RESPONSIBLE
1 | ReMCoDS request a business and technical contact from each Market Participant (MP) for cutover activities. | 2021-09-03 | 2021-09-03 | ReMCoDS
2 | MPs confirm contacts for cutover activities to ReMCoDS - each MP must provide a technical and business contact for the cutover activities. | 2021-09-10 | 2021-09-10 | All MPs
3 | Webforms installation Prerequisites document issued to MPs. | 2021-09-10 | 2021-09-10 | ReMCoDS
4 | NI MPs to execute Webforms installation Prerequisite steps. NI MPs must confirm to ReMCoDS that Webforms installation Prerequisite steps for their Production EMMA have been complete. | 2021-09-10 | 2021-09-17 | NI MPs
5 | ROI MPs to execute Webforms installation Prerequisite steps. ROI MPs must confirm to ReMCoDS that Webforms installation Prerequisite steps for their Production EMMA have been complete. | 2021-09-10 | 2021-09-24 | ROI MPs
6 | Cutover Workshop. | 2021-09-15 | 2021-09-15 | All
7 | ReMCoDS to provide a link to the latest Webforms software release and latest Webforms installation instructions. | 2021-09-17 | 2021-09-17 | ReMCoDS
8 | NI MPs to download and install New Webforms on NI Production EMMAs. NI MPs will need to engage with Atos to set up Webforms User Accounts. (Please note that ROI MPs will complete this task after the cutover weekend). | 2021-09-20 | 2021-09-23 | NI MPs
9 | MPs to complete Market Message (MM) reconciliation on a daily basis up to cutover. | 2021-09-20 | 2021-09-24 | All MPs
10 | Reminders sent to all MPs to stop sending MMs at 18:00 on Friday 24th September. Please ensure EMMA is left in normal operational mode for the weekend. | 2021-09-23 | 2021-09-24 | ReMCoDS
Cutover Weekend
No | KEY MARKET TASKS | START | FINISH | RESPONSIBLE
1 | MPs to stop sending MMs from this point. No further MMs until confirmation of resumption of services (Milestone 2). MPs may continue to receive messages from ESBN/NIEN until 20:00. | 2021-09-24 18:00 | 2021-09-24 18:00 | All MPs
2 | Tibco Hub Upgrade & Separation preparation activities. | 2021-09-24 18:00 | 2021-09-25 08:00 | Atos
3 | 602MM issued to MPs up to the point of Hub Shutdown for post cutover reconciliation purposes. | 2021-09-24 19:30 | 2021-09-24 20:00 | Atos
4 | Hub Upgrade & Separation starts. | 2021-09-25 08:00 | 2021-09-25 08:00 | Atos
5 | Hub Upgrade & Separation complete. | 2021-09-25 14:00 | 2021-09-25 14:00 | Atos
6 | Milestone 1: Notification Email: Upgrade & Separation complete. | 2021-09-25 14:00 | 2021-09-25 14:00 | ReMCoDS
7 | Network Operator Testing starts. | 2021-09-25 14:00 | 2021-09-25 14:00 | Atos
8 | Milestone 2: Notification Email: Network Operator Testing Complete (Point of no Return). Cutover is complete. Resumption of normal services. Dual Suppliers are advised, from this time, to point their back-end systems to the correct jurisdiction’s EMMA. | 2021-09-25 18:00 | 2021-09-25 18:00 | ReMCoDS
9 | Hypercare - MPs contact ReMCoDS if they encounter TIBCO related issues. Conference Call will be scheduled for Monday at 15:00 (27/09/2021). Hypercare plan will be issued 15th September. | 2021-09-25 18:00 | 2021-10-08 17:00 | ReMCoDS
Post Cutover Activity
No | KEY MARKET TASKS | START | FINISH | RESPONSIBLE
1 | All MPs to download and install latest Webforms Software release, issued 17th September, on their Test EMMAs if they have not yet done so. | 2021-10-21 | 2021-11-03 | All MPs
ROI Test & Production EMMA Activity
No | KEY MARKET TASKS | START | FINISH | RESPONSIBLE
ROI Test EMMAs
1 | ReMCoDS will advise ROI MPs of Test EMMA Webforms installation schedule, including Prerequisites, for any ROI Test EMMAs that have not yet had Webforms installed. | 2021-09-08 | 2021-09-08 | ReMCoDS
2 | ROI Test EMMA Webforms installation window. | 2021-09-13 | 2021-10-21 | ROI MPs
ROI Production EMMAs
3 | ROI MPs are provided with a time slot for their Production EMMA TIBCO Upgrade & Webforms Installation. | 2021-09-17 | 2021-09-17 | ReMCoDS
4 | ROI MPs confirm their availability for the proposed timeslot for their Production EMMA TIBCO Upgrade & Webforms Installation. | 2021-09-24 | 2021-09-24 | ROI MPs
5 | Atos will execute the TIBCO Upgrade for each ROI Production EMMA as per agreed schedule. Atos will contact each ROI MP directly on the day of their scheduled upgrade. Webforms installation Prerequisite steps must have been complete by 24th September. | 2021-09-29 | 2021-10-21 | Atos
6 | ROI MPs to download and install Webforms on ROI Production EMMA in alignment with their scheduled Production EMMA TIBCO Upgrade. ROI MPs will need to engage with Atos to set up Webforms User Accounts. | 2021-09-29 | 2021-10-21 | ROI MPs
7 | ReMCoDS send a notification to the Market once all ROI Production EMMA TIBCO Upgrades & Webforms Installations have completed. | 2021-10-21 | 2021-10-21 | ReMCoDS