## Sheet1
Task Name | Start | Finish | Resource | Area | Status
Planning
Publish Overall Retail Market IPT Plan on RMDS website | Mon 13/05/2024 | Mon 13/05/2024 | RMDS | IPT
IPT Test Collateral and Tool Preparation
RMDS send MP's Technical Connectivity Test checklist . | Mon 24/06/2024 | Mon 24/06/2024 | RMDS
Technical Connectivity test . | Mon 24/06/2024 | Fri 28/06/2024 | MP's | IPT
MPs submit to RMDS a completed Technical connectivity Checklist . | Mon 24/06/2024 | Fri 28/06/2024 | MP's
RMDS requests confirmation of IPT participants . | Fri 12/07/2024 | Fri 12/07/2024 | RMDS, MPs | IPT
MP's submit contact details of resource personnel assigned for IPT to RMDS. | Fri 12/07/2024 | Fri 19/07/2024 | MPs | IPT
Circulate V1.0 of IPT workbook to IPT Participants. | Mon 22/07/2024 | Mon 22/07/2024 | RMDS | IPT
Allow one week for IPT Participant review. | Mon 22/07/2024 | Fri 26/07/2024 | MPs | IPT
RMDS grants IPT Participants access to Evidence Storage Area. IPT Participants confirm access to Evidence Storage Area. | Mon 22/07/2024 | Fri 26/07/2024 | RMDS, MPs | IPT
Circulate V2.0 of IPT workbook to IPT Participants (including test data and Test Extranet access details). | Fri 16/08/2024 | Fri 16/08/2024 | RMDS | IPT
1 week Market Participant Data Preparation Window. | Mon 19/08/2024 | Fri 23/08/2024 | MPs | IPT
Send IPT Entry Criteria Checklist for IPT Participants. | Fri 16/08/2024 | Fri 16/08/2024 | RMDS | IPT
IPT Participants to send test market message(s) to prove end to end connectivity in advance of IPT start. Details to be included in the IPT Entry Criteria Checklist. | Fri 16/08/2024 | Mon 26/08/2024 | MPs | IPT
Receive confirmation from MPs that Checklist is completed | Mon19/08/2024 | Mon 26/08/2024 | MP's | IPT
RMDS to send MPs a Declaration of readiness form | Mon 26/08/2024 | Mon 26/08/2024 | RMDS | IPT
MP's return the completed Declaration of Readiness form to RMDS | Mon 26/08/2024 | Fri 30/08/2024 | MP's | IPT
IPT Execution Window | Mon 09/09/2024 | Fri 18/10/2024 | RMDS, Assurance Body, ESBN, MPs, Market Message Hub Support Team | IPT
IPT Test Execution | Mon 09/09/2024 | Fri 18/10/2024 | MPs | IPT
Issue IPT Findings Report to CRU | Wed 23/10/2024 | Wed 23/10/2024 | Assurance Body | IPT