## Slide 1: V14.00.00 Schema Release Roadmap v3.0
March 2024

## Slide 2: V14.00.00 Schema Release Roadmap - Approach
Market Schema Guide
  v14.00.00 Working v6.0 Draft 2 released 01/08/2023
Schema Release Strategy & Timeline
  The timeline below outlines the roadmap for the early release of draft v14.00.00 Schema during the Market Release Phase 2 project lifecycle
  The draft copies of the schema may be subject to corrections, should it be found necessary, as testing advances
  In the event of a change required to the schema as a result of a new approved market change, the timeline will be subject to review
  No schema will be released outside the planned timeline
  Each draft schema is issued for design/test purposes only and must not be applied to production market messaging environment prior to the v14.00.00 cutover
Draft 1 | End Nov 2022 | Issued | Initial draft post schema build, prior to validation/testing
Draft 2 | End Jul 2023 | Issued | Post validation checks
Draft 3 | End Mar 2024 |  | 
Draft 3.1 | End Apr 2024 |  | Placeholder should clarifications/corrections be required Post-SIT
Draft 4 | Aug 2024 |  | Final schema draft issued 3 months prior to go live (pre IPT Execution)
Final Schema | Nov 2024 |  | Issued post successful completion of IPT as part of Cutover readiness

## Slide 3: V14.00.00 Schema Release Roadmap - Approach
Release Content
  XSD Files
  Market Schema Guide v6.0 Working Draft 2 (Subsequent drafts will be aligned to MCR Revisioning activity as required)
  Release Notes and Caveats
Version Control Process
  Draft schemas may be subject to correction (as outlined In Release Strategy on previous slide)
  Release notes will issue with each draft detailing any corrections
  Schema drafts will be released as per agreed timeline
Approach communicated with all relevant parties
  RMDS, Market Participants
Method of Sharing Schema
  RMDS will issue each draft schema
Supplier Queries
  All queries to be directed to RMDS@esb.ie using standard template marked as ‘Schema’

## Slide 4: v14.00.00 Schema Release Timeline
2022 |  |  |  |  | 2023 |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  | 
Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Schema Drafts
V14.00.00
High Level
Plan
Schema Sharing
Roadmap
Approach
Final Schema
MAR 2024
Market Schema
Guide
Go Live
Q3 2024
Draft 3
Draft 4
v14 Working
V6 Draft 1
Publish Draft Schema Sharing Approach via RMDS
v14.00.00 Schema Final (For Cutover)
Draft 2
Design, Build & Test
Plan
& Prep
Exec
IPT Window
Publish Updated Draft Schema Sharing Approach v2.0 via RMDS
Draft 1
(Issued Nov 2022)
Hypercare
Draft 3.1
v14 Working
V6 Draft 2
Publish Updated Draft Schema Sharing Approach v3.0 via RMDS
LEGEND
Key Milestone
Placeholder
Go Live