## Sheet1
Task Name | Start | Finish | Resource | Area | Status
Planning
Publish Overall Retail Market IPT Plan on RMDS website | Fri 11/12/20 | Fri 11/12/20 | RMDS | IPT | Complete
IPT Test Collateral and Tool Preparation
Circulate V1.0 of Market Participant IPT workbook | Fri 11/12/20 | Fri 11/12/20 | RMDS | IPT | Complete
Circulate V2.0 of Market Participant IPT workbook (including test data) | Thur 17/12/20 | Thur 17/12/20 | RMDS | IPT | Scheduled
Market Participant Data Prep Window | Thur 17/12/20 | Fri 08/01/21 | MPs | IPT | Scheduled
Send IPT Entry Criteria Checklist for MPs | Tue 05/01/21 | Tue 05/01/21 | RMDS | IPT | Scheduled
Receive confirmation from MPs that Checklist is completed | Tue 05/01/21 | Fri 08/01/21 | RMDS, MPs | IPT | Scheduled
IPT Execution
IPT Execution Window | Mon 11/01/21 | Fri 22/01/21 | All | IPT | Scheduled
Assurance Final Outcome Report Phase | Mon 25/01/21 | Wed 10/02/21 | Gemserv, CRU | IPT | Scheduled
Go/No Go Decision | Wed 10/02/21 | Wed 10/02/21 | CRU | IPT | Scheduled