## Sheet1
Task Name | Start | Finish | Resource | Area | Status
Planning
Publish Overall Retail Market IPT Plan on RMDS website | Fri 02/10/20 | Fri 02/10/20 | RMDS | IPT | Complete
IPT Test Collateral and Tool Preparation
Circulate V1.0 of Market Participant IPT workbook | Mon 06/09/20 | Mon 06/09/20 | RMDS | IPT | Complete
Allow one week for MP review | Mon 06/09/20 | Mon 13/09/20 | RMDS, MPs | IPT | Complete
Circulate V2.0 of Market Participant IPT workbook | Mon 21/09/20 | Mon 21/09/20 | RMDS | IPT | Complete
RMDS grants MPs access to Evidence Storage Area. MPs confirm access to Evidence Storage Area. | Mon 05/10/20 | Mon 12/10/20 | RMDS, MPs | IPT | Scheduled
Circulate V3.0 of Market Participant IPT workbook (including test data) | Mon 12/10/20 | Mon 12/10/20 | RMDS | IPT | Scheduled
2 week Market Participant Data Prep Window | Mon 12/10/20 | Mon 26/10/20 | MPs | IPT | Scheduled
RMDS to inform MPs when the IPT environment is available | Mon 19/10/20 | Mon 19/10/20 | RMDS | IPT | Scheduled
Test Extranet access details included in MPs Workbook | Mon 19/10/20 | Mon 19/10/20 | RMDS | IPT | Scheduled
Send IPT Entry Criteria Checklist for MPs | Tue 20/10/20 | Fri 23/10/20 | RMDS | IPT | Scheduled
Receive confirmation from MPs that Checklist is completed | Tue 20/10/20 | Fri 23/10/20 | RMDS, MPs | IPT | Scheduled
IPT EMMA Preparation
Supplier workshop (Skype) to walk through the EMMA upgrade process (MP attendance mandatory) | Wed 30/09/20 | Wed 30/09/20 | Atos | IPT | Complete
Inform MPs of timeslot for IPT EMMA upgrade | Mon 05/10/20 | Mon 05/10/20 | ReMCoDS | IPT | Scheduled
Confirm Connectivity for IPT EMMA @ V12.00.00 | Mon 05/10/20 | Mon 05/10/20 | MPs | IPT | Scheduled
Atos upgrade IPT Test EMMA for Market Participants | Mon 12/10/20 | Mon 12/10/20 | Atos | IPT | Scheduled
MPs provide support to Atos during upgrade window | Mon 12/10/20 | Mon 12/10/20 | MPs | IPT | Scheduled
ReMCoDS to inform each MP of successful upgrade | Mon 12/10/20 | Mon 12/10/20 | ReMCoDS | IPT | Scheduled
ReMCoDS to inform MPs when upgrades are complete | Mon 12/10/20 | Mon 12/10/20 | ReMCoDS | IPT | Scheduled
IPT Execution | Tue 27/10/20 | Mon 23/11/20 | RMDS, Gemserv, ESBN, MPs, Atos | IPT | Scheduled
Issue final assurance outcome report to CRU | Fri 11/12/20 | Fri 11/12/20 | Gemserv | IPT | Scheduled
Schema
Send V13.00.00 schema files to MPs | December 2020 | December 2020 | ReMCoDS | Schema Release | Scheduled